## Scope
Project Name | : | Cost Code Project
Project Owner | : | Aditya Yoga
Project Sponsor | : | Aan Akhmad Prayoga
Stakeholders | : | Aan Akhmad Prayoga, Aditya Yoga, M Irfan, Afrani, Siti, M Abdul Kadir, Bagus A, Hastono
Project Goals | : | Cost control and cost monitoring time basis for budget and actual of Andesite Project
Problem statement | : | To meet the needs of cost controlling and cost monitoring Budget and Actual expense in timeline basis from Andesit Project, it requires the system that fit with those needs
Project Charter
|  | Roles | Responsibilities | Stakholders
|  | DE | Decide project execution | Aan
|  | DRB | Review and recommend to DE regarding project planning and execution | Aan, hastono, bagus, irfan
|  | Business Analyst | Translate business needs into some requirement (product design, requirement, flow process) | Yoga, rani, siti
|  | Developer | Develop feature and requirement into executable software | Yoga, Adi
|  | Resources | - | Irfan
Project Deliverables | : | Product Planning Product design product documentation Executable product Product Timeline
Milestones | : | Release Product Planning |  | 2014-05-19
|  | Release Product Design incl. product backlog |  | 2014-05-21
|  | Release Executable product phase 1(testing 1) |  | 2014-05-26
|  | Release Executable product phase 2 (testing 2) |  | 2014-05-29
|  | Final release |  | 2014-06-05
Cost Estimates | : | TBD

## Product Info
Cost Center Dashboard
Author/Developer | Mohamad Abdul Kadir, Yoga
Date | -
Version | -
Model Purpose
-
-
-
Assumptions
-
-
Table of Contents
-
Version Comments
0.1 | Product testing 1
0.2 | Product testing 2
1 | Product release